MG # 7

Panel

Statistics

Cutting start date 06/03/2006

Cutting complete

11/08/2006 (159days)

Total metres cut

7421m

Average Engineering availability

91.8%

Average operating time

78 hrs per week

Average operational

Availability

77.6%

Average meters per week

340 mts

Av 47m/day

Average cut rate

4.2 mts per hour

Scheduled section advance                    530 hrs

Mechanical scheduled maintenance      137 hrs

Moving flitting                                       132 hrs

Related equipment down                       65 hrs

Extra Travel                                            60 hrs

Stonedusting                                           50   hrs

Average Belt move time  17.8 hrs

Safety Statistics

LTI,s                                                               1

Restricted Work Injuries                             1

Medical Treatments                                      0

First aid Injuries                                          15

Report Only                                                  10

High Potential Risk Incident                 0

Dev Budget Complete MG7   17/08/06

Dev CMPS Complete MG7   11/08/06

LW Budget complete MG6    22/09/06

LW CMPS completion MG6   8/10/06

Float 58 days

50

--